## Execution Summary
OrangeHRM — Execution Summary
Management-level execution snapshot derived from the same 96-case canonical baseline and linked defect register.
Metric | Result |  | QA Disposition
Total Test Cases | 96 |  | Execution is complete for the historical baseline, but test closure is pending. Four failed cases require controlled reproduction because exact historical evidence was not retained. BUG-004 is both High severity and High priority and is present on the Critical Path suite. Recommended disposition: reproduce and triage BUG-001 to BUG-004 before final closure reporting.
Executed | 96
Passed | 92
Failed | 4
Blocked | 0
Not Executed | 0
Execution % | 100%
Pass % | 95.83%
Open Defects | 4
High-Severity Defects | 2
Bug ID | Test Case ID | Module | Severity | Priority | Status | Retest | Next Action
BUG-001 | TC-LGN-012 | Login | Medium | Medium | Open - Needs Reproduction | Pending | Reproduce credential casing behavior.
BUG-002 | TC-FGP-003 | Forgot Password | High | Medium | Open - Needs Reproduction | Pending | Capture unknown-user password reset response.
BUG-003 | TC-REC-005 | Recruitment | Medium | Medium | Open - Needs Reproduction | Pending | Re-test malformed candidate email validation.
BUG-004 | TC-MYI-004 | My Info | High | High | Open - Needs Reproduction | Pending | Verify ESS Job/Salary authorization controls.
Evidence & Reporting Controls
Execution source | Historical source workbook retained; no execution dates/browser/build values were invented.
Environment | ENV-DEMO-01 — OrangeHRM Demo.
Defect control | Failed cases linked to Defect_Log.xlsx and the final RTM.
Screenshot evidence | No historical screenshots were supplied; capture during reproduction/retest.
Closure dependency | Final Test Summary should reflect defect reproduction and disposition status.

## Module Metrics
OrangeHRM — Execution Metrics by Module
Module-level result distribution used for execution reporting and closure analysis.
Module | Total | Executed | Passed | Failed | Blocked | Not Executed | Execution % | Pass % | Defects
Login | 12 | 12 | 11 | 1 | 0 | 0 | 100% | 91.67% | 1
Forgot Password | 5 | 5 | 4 | 1 | 0 | 0 | 100% | 80% | 1
Dashboard | 5 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0
Admin | 10 | 10 | 10 | 0 | 0 | 0 | 100% | 100% | 0
PIM | 16 | 16 | 16 | 0 | 0 | 0 | 100% | 100% | 0
Leave | 10 | 10 | 10 | 0 | 0 | 0 | 100% | 100% | 0
Time | 8 | 8 | 8 | 0 | 0 | 0 | 100% | 100% | 0
Recruitment | 8 | 8 | 7 | 1 | 0 | 0 | 100% | 87.5% | 1
My Info | 6 | 6 | 5 | 1 | 0 | 0 | 100% | 83.33% | 1
Performance | 5 | 5 | 5 | 0 | 0 | 0 | 100% | 100% | 0
Directory | 4 | 4 | 4 | 0 | 0 | 0 | 100% | 100% | 0
Buzz | 3 | 3 | 3 | 0 | 0 | 0 | 100% | 100% | 0
Session | 4 | 4 | 4 | 0 | 0 | 0 | 100% | 100% | 0