## Suite Overview
OrangeHRM — Post-Fix Sanity Test Suite
Targeted verification suite for bug-fix validation and immediate regression confidence.
Suite Metric | Value |  | Execution Control
Planned sanity cases | 20 |  | Trigger: execute after fixes are deployed for the four historical failure areas. Primary retests: TC-LGN-012, TC-FGP-003, TC-REC-005 and TC-MYI-004. Guardrails: adjacent authentication, password reset, user/role, recruitment and session flows are included to detect immediate side effects. Entry criteria: fix build available; smoke gate passed or formally waived; required Admin and ESS accounts available. Exit criteria: all 20 cases executed; all four primary retests pass or are re-triaged; no new Critical/High regression introduced.
Historical failed cases targeted | 4
Impact guardrail cases | 16
Modules covered | 7
Execution status | Not Executed
Fix Cluster | Primary Retest | Supporting Guardrails | Reason
Authentication case sensitivity | TC-LGN-012 | TC-LGN-001, TC-LGN-002, TC-LGN-003, TC-LGN-004, TC-SES-001 | Confirms the credential-case fix does not break valid/invalid login handling or session termination.
Forgot Password account privacy | TC-FGP-003 | TC-FGP-001, TC-FGP-002 | Confirms invalid-account handling while preserving normal reset navigation and valid-user behavior. | Module | Case Count | % of Suite
Recruitment email validation | TC-REC-005 | TC-REC-001, TC-REC-002, TC-REC-004 | Confirms email validation without disrupting candidate creation, required-field validation or module availability. | Login | 5 | 25%
My Info role permissions | TC-MYI-004 | TC-MYI-001, TC-MYI-005, TC-ADM-001, TC-ADM-002, TC-ADM-009, TC-PIM-005 | Confirms ESS restrictions and surrounding user/role/login-detail administration remain functional. | Forgot Password | 3 | 15%
|  |  |  | Admin | 3 | 15%
|  |  |  | PIM | 1 | 5%
Status Rule | Meaning | Action |  | Recruitment | 4 | 20%
Not Executed | Prepared for post-fix sanity cycle | Execute only against the designated fix build. |  | My Info | 3 | 15%
Primary retest | Historically failed baseline behavior | Must pass or be re-triaged before sanity closure. |  | Session | 1 | 5%
Impact guardrail | Historically passing adjacent behavior | Used to detect immediate regression side effects.

## Sanity Test Suite
OrangeHRM — Post-Fix Sanity Test Suite
20 targeted cases selected from the 96-case canonical baseline. Four primary retests + sixteen impact guardrails.
Execution state: Not Executed. Browser, build, executor, date and actual result must be captured when the post-fix sanity cycle is run.
Requirement ID | Test Case ID | Module | Feature | Test Scenario | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Severity | Type | Status | Executed By | Execution Date | Environment | Browser | Build Version | Comments
RQ-LGN-001 | TC-LGN-001 | Login | Login Page | TS-LGN-001 — Verify login page loads correctly | OrangeHRM Demo login page is reachable and the user is logged out. | 1. Navigate to application URL. | N/A | Login page displays with Username, Password fields, Login button, OrangeHRM logo. | Pending sanity execution against the post-fix build. | High | High | UI / Navigation | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 01/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-LGN-002 | TC-LGN-002 | Login | Authentication | TS-LGN-002 — Verify successful login with valid credentials | OrangeHRM Demo login page is reachable; active Admin credentials are available; user is logged out. | 1. Enter valid username. 2. Enter valid password. 3. Click Login. | Admin/admin123 | User redirected to Dashboard page. | Pending sanity execution against the post-fix build. | High | Critical | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 02/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-LGN-003 | TC-LGN-003 | Login | Authentication | TS-LGN-003 — Verify login fails with invalid username | OrangeHRM Demo login page is reachable; a valid password is available; user is logged out. | 1. Enter invalid username. 2. Enter valid password. 3. Click Login. | wronguser/admin123 | Error message "Invalid credentials" displayed. | Pending sanity execution against the post-fix build. | High | High | Functional - Negative | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 03/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-LGN-003 | TC-LGN-004 | Login | Authentication | TS-LGN-003 — Verify login fails with invalid password | OrangeHRM Demo login page is reachable; a valid username is available; user is logged out. | 1. Enter valid username. 2. Enter invalid password. 3. Click Login. | Admin/wrongpass | Error message "Invalid credentials" displayed. | Pending sanity execution against the post-fix build. | High | High | Functional - Negative | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 04/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-LGN-009 | TC-LGN-012 | Login | Credential Case Sensitivity | TS-LGN-009 — Verify case sensitivity of username/password | OrangeHRM Demo login page is reachable; active credentials with known letter casing are available; user is logged out. | 1. Enter username/password in different case. | ADMIN/ADMIN123 | Login fails if credentials are case-sensitive. | Pending sanity execution against the post-fix build. | Medium | Medium | Functional - Negative | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 05/20. Primary retest for historical failed baseline case. Baseline status: Fail. Execute only after the related fix is available; capture defect ID, actual result, browser, build and evidence during execution.
RQ-FGP-001 | TC-FGP-001 | Forgot Password | Reset Password Page | TS-FGP-001 — Verify reset password page loads | OrangeHRM Demo login page is reachable and the user is logged out. | 1. Click Forgot your password link. | N/A | Reset Password page with Username field displayed. | Pending sanity execution against the post-fix build. | Medium | Medium | UI / Navigation | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 06/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-FGP-002 | TC-FGP-002 | Forgot Password | Reset Request | TS-FGP-002 — Verify password reset request with valid username | Reset Password page is open and a registered username is available. | 1. Enter registered username. 2. Click Reset Password. | Admin | Confirmation message "Reset Password link sent successfully". | Pending sanity execution against the post-fix build. | High | High | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 07/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-FGP-003 | TC-FGP-003 | Forgot Password | Account Privacy | TS-FGP-003 — Verify password reset request with invalid username | Reset Password page is open and a deliberately unregistered username is available. | 1. Enter unregistered username. 2. Click Reset Password. | invaliduser123 | Appropriate message displayed without exposing user existence. | Pending sanity execution against the post-fix build. | Medium | High | Security-Oriented | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 08/20. Primary retest for historical failed baseline case. Baseline status: Fail. Execute only after the related fix is available; capture defect ID, actual result, browser, build and evidence during execution.
RQ-ADM-001 | TC-ADM-001 | Admin | System Users | TS-ADM-001 — Verify Admin module page loads with System Users list | Administrator is authenticated and has access to the Admin module. | 1. Navigate to Admin tab. | N/A | System Users grid displayed with existing users. | Pending sanity execution against the post-fix build. | High | High | UI / Navigation | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 09/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-ADM-002 | TC-ADM-002 | Admin | System User Creation | TS-ADM-002 — Verify adding a new system user with valid data | Administrator is authenticated; Admin > System Users is accessible; an eligible employee exists; a unique test username is available. | 1. Click Add. 2. Select User Role, Employee Name, Status. 3. Enter Username & Password. 4. Click Save. | Role: ESS, valid employee, unique username | New user created and listed in System Users grid. | Pending sanity execution against the post-fix build. | High | High | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 10/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-ADM-009 | TC-ADM-009 | Admin | User Filtering | TS-ADM-009 — Verify search filter by User Role and Status | Administrator is authenticated; System Users contains records matching the selected role/status combination. | 1. Select Role = Admin, Status = Enabled. 2. Click Search. | Role: Admin, Status: Enabled | Only users matching both criteria displayed. | Pending sanity execution against the post-fix build. | Medium | Medium | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 11/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-PIM-005 | TC-PIM-005 | PIM | Employee Login Details | TS-PIM-005 — Verify creating login details for an employee | Administrator is authenticated; PIM > Add Employee is accessible; unique ESS username/password test data is available. | 1. Add employee. 2. Enable Create Login Details toggle. 3. Enter username/password. 4. Save. | Valid credentials | Employee created with ESS login access. | Pending sanity execution against the post-fix build. | High | High | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 12/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-REC-001 | TC-REC-001 | Recruitment | Candidates List | TS-REC-001 — Verify Recruitment module loads Candidates list | Authenticated user has access to the Recruitment module. | 1. Navigate to Recruitment tab. | N/A | Candidate list grid displayed. | Pending sanity execution against the post-fix build. | High | High | UI / Navigation | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 13/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-REC-002 | TC-REC-002 | Recruitment | Candidate Creation | TS-REC-002 — Verify adding a new candidate with valid details | Authorized user is authenticated; Recruitment > Candidates is accessible; an active vacancy is available. | 1. Click Add. 2. Enter Name, Email, Vacancy. 3. Save. | John Smith, valid email, vacancy selected | Candidate added to Candidates list. | Pending sanity execution against the post-fix build. | High | High | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 14/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-REC-004 | TC-REC-004 | Recruitment | Required Field Validation | TS-REC-004 — Verify mandatory field validation on Add Candidate | Authorized user is authenticated and the Add Candidate form is open. | 1. Click Save without Name/Email. | N/A | Required validation messages shown. | Pending sanity execution against the post-fix build. | High | High | Functional - Negative | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 15/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-REC-005 | TC-REC-005 | Recruitment | Email Validation | TS-REC-005 — Verify invalid email format validation | Authorized user is authenticated and the Add Candidate form is open. | 1. Enter invalid email format. 2. Save. | john.smith (no domain) | Error: "Expected format not matched". | Pending sanity execution against the post-fix build. | Medium | Medium | Functional - Negative | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 16/20. Primary retest for historical failed baseline case. Baseline status: Fail. Execute only after the related fix is available; capture defect ID, actual result, browser, build and evidence during execution.
RQ-MYI-001 | TC-MYI-001 | My Info | Personal Details | TS-MYI-001 — Verify My Info displays logged-in employee's personal details | Authenticated employee has access to My Info. | 1. Navigate to My Info. | N/A | Personal details of logged-in user displayed. | Pending sanity execution against the post-fix build. | High | High | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 17/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-MYI-004 | TC-MYI-004 | My Info | Role Permissions | TS-MYI-004 — Verify My Info restricts editing of Job/Salary details for ESS user | ESS user account is available and authenticated; My Info > Job/Salary areas are accessible for permission verification. | 1. Login as ESS user. 2. Navigate to Job tab. | ESS user login | Fields read-only/restricted based on permission. | Pending sanity execution against the post-fix build. | High | High | Role / Permission | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 18/20. Primary retest for historical failed baseline case. Baseline status: Fail. Execute only after the related fix is available; capture defect ID, actual result, browser, build and evidence during execution.
RQ-MYI-005 | TC-MYI-005 | My Info | Change Password | TS-MYI-005 — Verify Change Password functionality from My Info/Profile | Authenticated user knows the current password and can access Change Password. | 1. Click profile dropdown. 2. Select Change Password. 3. Enter current & new password. 4. Save. | Valid current password, new password | Password updated successfully, re-login required. | Pending sanity execution against the post-fix build. | High | High | Functional - Positive | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 19/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.
RQ-SES-001 | TC-SES-001 | Session | Logout | TS-SES-001 — Verify successful logout redirects to Login page | User is authenticated and an active session exists. | 1. Click profile dropdown. 2. Click Logout. | N/A | User logged out and redirected to Login screen. | Pending sanity execution against the post-fix build. | High | High | Session / Access Control | Not Executed | Pending |  | OrangeHRM Demo — post-fix sanity cycle | To be captured at execution | To be captured at execution | Sanity sequence 20/20. Impact guardrail selected to verify adjacent behavior around the four historical failure areas. Baseline status: Pass. Re-execute after fixes to detect unintended side effects.